## Slide 1: 8-Step Training Model - Managing A Precious Resource
By
[State your name]
  “I know of no better reputation for an officer or noncommissioned officer to have with his men than he is a good manager and does not waste his soldiers’ time.”
––GEN Bruce Clarke

## Slide 2: References
FM 7-0 Training the Force
FM 5-19 Composite Risk Management

## Slide 3
Purpose of the 8-Step Training Model
Anatomy of the 8-Step Training Model
  Plan the Training
  Train and Certify the Leaders
  Recon the Site
  Issue the Plan
  Rehearse
  Execute
  Conduct an AAR
  Retrain
Example use of 8-Step Training Model
Conclusion
Agenda

## Slide 4
To provide a standard method by which leaders may properly plan and execute effective training.
  Effects proper resource management
A tool to help you give your Soldiers the training they deserve
Put the 8-Step Training Model on the Calendar
Purpose of the 8-Step Training Model

## Slide 5: The 8-Step Training Model
Retrain
Rehearse
Issue
Plan
Recon
Site
Conduct
AAR
Train and
Certify Leaders
PLAN
TRAINING
Execute

## Slide 6: 8-Step Training Model (1 of 8) Plan the Training
Time is a precious commodity to ARNG units - there is time to train but no time to waste.
Training strategy must be battle-focused and METL driven.
Develop clear training objectives and a way to measure your progress toward proficiency in a given task.
Multi-echelon training.
Begin Risk Management
Creatively plan training events to maximize the training

## Slide 7: 8-Step Training Model (2 of 8) Train & Certify Leaders
Have a training methodology to execute and develop leaders as superb trainers.
Leader training not only ensures the leader knows how to perform the task, it also allows the leader to decide the best way to train the task.
By training, coaching, and mentoring our leaders we
  Set them up for success
  Shape them professionally
Give them the confidence born from competence

## Slide 8: 8-Step Training Model (3 of 8) Recon the Site
Reconnaissance allows the leader to determine whether a site is suitable for a specific training event.
Leader’s reconnaissance must be extremely detailed as site selection and layout are critical to success.
Identify what needs to happen (implied tasks) to prepare for the training event, given the location.
Refine Risk Management.
Ensures the training is a success

## Slide 9: 8-Step Training Model (4 of 8) Issue the Plan
The plan is usually stated in the form of a five paragraph OPORD
Expressing orders in standard formats containing essential. elements, ensures that instructions are conveyed clearly, concisely, and completely.
Refine Risk Management – what can go wrong will. Plan for it.
Clearly state your intent in a way that is easy to understand.

## Slide 10: 8-Step Training Model (5 of 8) Rehearse
If leaders can visually conceptualize the task, they will no doubt execute better when the time comes.
Allows a chance to “work out the kinks” or eliminate any problems that may distract training.
Well directed rehearsals help soldiers become familiar with what they must do. A good way to rehearse is to have the leader walk and talk the soldiers through each action.
Refine Risk Management
Helps to ensure maximum effectiveness of training.

## Slide 11: 8-Step Training Model (6 of 8) Execute
We must continually emphasize training to standard, not time.
Allow adequate time between events for preparation of the next event.
Keep good communication.
Supervise training execution.
Implement Risk mitigation steps.
The payoff of your planning and preparation

## Slide 12: 8-Step Training Model (7 of 8) Conduct an AAR
We must master the “how to” of the after action review. It is a critical to the assessment phase as well as determining what to train next.
Establish environment of “OK for honesty – no retribution”
This gives the chance for leaders and soldiers to give valuable input and express their feelings about the previous training.
Be candid, be frank, be brutally honest. Put all pride aside and discuss what went well and, more importantly, what needs to be improved on.
We don’t have time to be anything but honest!

## Slide 13: 8-Step Training Model (8 of 8) Retrain
If the unit does not demonstrate sufficient proficiency after training, they must be retrained.
Substandard performance will result in retraining.
We owe it to them as leaders.
Would you want to be left insufficiently trained, if your life depended on the training?

## Slide 14: Timeline of 8-Step Training Model
Issue
Plan
Recon
Site
Conduct
AAR
Rehearse
Train and
Certify Leaders
PLAN
TRAINING
Execute
Retrain
PLAN
TRAINING
Not necessarily sequential
Time

## Slide 15: Example: Urban Operations Instruction (08-09 Aug 09).
Action: Discuss the preparation timeline for the Urban Operations Instruction (08-09 Aug 09).
Conditions: Using the 8-Step Training Model, a group facilitator/presenter and audience in a classroom environment
Standards: Timeline must account for all steps of the 8-step training model; 5 minutes or less

## Slide 16: Assumptions
Live fire ranges and training areas will be utilized
Training areas to plan for:
  Urban characteristics, soldier and unit considerations
  Urban ops in buildings, individual ops
  Urban ops in 4-Soldier teams
  Squad urban ops
  Vehicle urban ops
  Range ops (safeties, OIC, NCOICs)

## Slide 17: Urban Ops Instruction
Issue
Plan
Recon
Site
Conduct
AAR
Rehearse
Train and
Certify Leaders
PLAN
TRAINING
Execute
Retrain
PLAN
TRAINING
All of this can be on your training schedules
Backwards planning
Aug & Sep 09
08 & 09 Aug 09
08-09 Aug 09
18-19 Jul 09
Jun 09 (AT)
May 09
Jun 09 (AT)
Apr 09
Aug 08
Oct 09
Urban characteristics, soldier and unit considerations
Urban ops - individual ops
Urban ops in 4-Soldier teams
Squad urban ops
Vehicle urban ops
Range ops (safeties, OIC, NCOICs)
Other?
Urban characteristics, soldier and unit considerations
Urban ops - individual ops
Urban ops in 4-Soldier teams
Squad urban ops
Vehicle urban ops
Range ops (safeties, OIC, NCOICs)
Other?
Planning includes resource coordination, FRAGOS, etc.

## Slide 18: Tools available
8-Step Training Model Checklist
Fill it out with every training event
Modify as needed

## Slide 19: In Closing…
Your second most precious asset is time – it’s like money, and it’s worth spending to ensure you have good training for your soldiers.
8-step Training model can help you spend it wisely.

## Slide 20: Questions? / Issues!