## TIMELINE BASELINE
BRIDADE MDMP |  | ALLOTTED TIMES
MISSION ANALYSIS 30% | MISSION ANALYSIS (MA) STARTS
ASCOPE WORKSHEET TURN IN
MA 1 BRIEF REHEARSAL PREP
MA 1 BRIEF REHEARSAL & ADJUSTMENTS
MA 1 BRIEF
REVERSE WFF WORKSHEET TURN IN
MA WORKSHEET TURN IN
MA BRIEF 2 REHEARSAL PREP
MA BRIEF 2 REHEARSAL & ADJUSTMENTS
MISSION ANALYSIS 2 BRIEFING
COMMANDER'S TIME
COMMANDER'S GUIDANCE
COA DEV 20% | COA DEVELOPMENT
COA BRIEF REHEARSAL & ADJUSTMENTS
COA BRIEF
WAR-GAMING 30% | PREP FOR WARGAME
WARGAME
COA COMPARISON/DECISION
OPORD DEV 20% | OPORD/ANNEXES DEVELOPMENT
XO REVIEW/RECONCILIATION
OPORD BRIEFING REHEARSAL & ADJUSTMENTS
OPORD BRIEFING
Sub. CDR Confirmation Briefs
Sub. CDR Backbriefs
BRIGADE REHEARSAL/COMMEX
| BDE ISR REHEARSAL |  | REHEARSALS CANNOT START UNTIL BATTALIONS HAVE COMPLETED WARGAMING AND CDR HAS APPROVED THEIR COA OR 80% OF BN MDMP AVAILABLE TIME
BDE FS REHEARSAL
BDE SUSTAINMENT REHEARSAL
CAR REHEARSAL
BDE COMMEX
BATTALION MDMP |  | ALLOTTED TIMES
MISSION ANALYSIS 30% | MISSION ANALYSIS (MA) STARTS
ASCOPE WORKSHEET TURN IN
MA 1 BRIEF REHEARSAL PREP
MA 1 BRIEF REHEARSAL & ADJUSTMENTS
MA 1 BRIEF
REVERSE WFF WORKSHEET TURN IN
MA WORKSHEET TURN IN
MA BRIEF 2 REHEARSAL PREP
MA BRIEF 2 REHEARSAL & ADJUSTMENTS
MISSION ANALYSIS 2 BRIEFING
COMMANDER'S TIME
COMMANDER'S GUIDANCE
COA DEV 20% | COA DEVELOPMENT
COA BRIEF REHEARSAL & ADJUSTMENTS
COA BRIEF
WAR-GAMING 30% | PREP FOR WARGAME
WARGAME
COA COMPARISON/DECISION
OPORD DEV 20% | OPORD/ANNEXES DEVELOPMENT
XO REVIEW/RECONCILIATION
OPORD BRIEFING REHEARSAL & ADJUSTMENTS
OPORD BRIEFING
Sub. CDR Confirmation Briefs
Sub. CDR Backbriefs
COMPANY TROOP LEADING STEPS
COMPANY/TROOP/BATTERY ACTIVITY
Make Tentative Plan
Initiate Movement
Conduct Recon
Complete Plan
Issue OPORD
Briefbacks
Inspections
Rehearsals
Mission Execution

## TIMELINE CALCULATOR
| AVAILABLE HOURS FOR BDE MDMP = | 100 |  | DURATION UNTIL NEXT EVENT |  | MDMP HRS AVAILABLE
BRIGADE MDMP |  | ADJUSTED TIMES | TIME ACTIVITY STARTS | DURATION HR:MIN | DURATION (HRS AS DECIMAL) | HOURS
MISSION ANALYSIS 30% | MISSION ANALYSIS (MA) STARTS |  | 2011-02-01 15:30 | 4:00 | 4 | 30 | STEP | INSTRUCTIONS
| ASCOPE WORKSHEET TURN IN |  | 2011-02-01 19:30 | 2:00 | 2 |  | 1 | XO CALCULATES TIME AVAILABLE FOR BDE MDMP | 1/3 OF (MISSION EXECUTION-MDMP START TIME)
| MA 1 BRIEF REHEARSAL PREP |  | 2011-02-01 21:30 | 2:00 | 2 |  | 2 | XO COMPLETES CELL C1, D3 AND BLUE SHADED CELLS
| MA 1 BRIEF REHEARSAL & ADJUSTMENTS |  | 2011-02-01 23:30 | 2:00 | 2 |  | 3 | XO ADJUSTS FOR SLEEP TIME, CLASSES, ETC
| MA 1 BRIEF |  | 2011-02-02 01:30 | 1:00 | 1
| SLEEP TIME |  | 2011-02-02 02:30 | 6:00 | 6
| REVERSE WFF WORKSHEET TURN IN |  | 2011-02-02 08:30 | 2:00 | 2 |  |  | In this example the BDE had 300 hours from receipt of mission until execution. The Brigade took 1/3 or 100 hours for MDMP, that left 200 hours for the Battalions, who took 1/3 or 66 hours for MDMP.
| MA WORKSHEET TURN IN |  | 2011-02-02 10:30 | 3:00 | 3
| MA BRIEF 2 REHEARSAL PREP |  | 2011-02-02 13:30 | 3:00 | 3
| MA BRIEF 2 REHEARSAL & ADJUSTMENTS |  | 2011-02-02 16:30 | 2:00 | 2
| MISSION ANALYSIS 2 BRIEFING |  | 2011-02-02 18:30 | 2:00 | 2 |  |  | XO Inserted SLEEP TIME on row and adjusted other times accordingly
| COMMANDER'S TIME |  | 2011-02-02 20:30 | 0:45 | 0.75
| COMMANDER'S GUIDANCE |  | 2011-02-02 21:15 | 0:15 | 0.25
COA DEV 20% | SLEEP TIME |  | 2011-02-02 21:30 | 8:00 | 8 | 20
| COA DEVELOPMENT |  | 2011-02-03 05:30 | 7:00 | 7
| COA BRIEF REHEARSAL & ADJUSTMENTS |  | 2011-02-03 12:30 | 3:00 | 3
| COA BRIEF |  | 2011-02-03 15:30 | 2:00 | 2
WAR-GAMING 30% | PREP FOR WARGAME |  | 2011-02-03 17:30 | 2:00 | 2 | 30
| WARGAME |  | 2011-02-03 19:30 | 8:00 | 8
| SLEEP TIME |  | 2011-02-04 03:30 | 4:00 | 4
| WARGAME CONTINUED |  | 2011-02-04 07:30 | 8:00 | 8
| COA COMPARISON/DECISION |  | 2011-02-04 15:30 | 8:00 | 8
OPORD DEV 20% | SLEEP TIME |  | 2011-02-04 23:30 | 6:00 | 6 | 20
| OPORD/ANNEXES DEVELOPMENT |  | 2011-02-05 05:30 | 6:00 | 6
| XO REVIEW/RECONCILIATION |  | 2011-02-05 05:30 | 2:00 | 2
| OPORD BRIEFING REHEARSAL & ADJUSTMENTS |  | 2011-02-05 07:30 | 2:00 | 2
| OPORD BRIEFING |  | 2011-02-05 09:30 | 2:00 | 2
| Sub. CDR Confirmation Briefs |  | 2011-02-05 11:30 | 2:00 | 2
| Sub. CDR Backbriefs |  | 2011-02-05 13:30 | 1:00 | 1
BRIGADE REHEARSAL/COMMEX
| BDE ISR REHEARSAL |  |  | REHEARSALS CANNOT START UNTIL BATTALIONS HAVE COMPLETED WARGAMING AND CDR HAS APPROVED THEIR COA OR 80% OF BN MDMP AVAILABLE TIME
BDE FS REHEARSAL
BDE SUSTAINMENT REHEARSAL
CAR REHEARSAL
BDE COMMEX
| BN MDMP AVAILABLE HRS | 66
| 30% | 19.8
| 20% | 13.2
BATTALION MDMP |  | ADJUSTED TIMES | TIME ACTIVITY STARTS | DURATION HR:MIN | DURATION (HRS AS DECIMAL) | 66 HRS
MISSION ANALYSIS 30% | MISSION ANALYSIS (MA) STARTS |  | 2011-02-05 13:30 | 1:00 | 1 | 19.8 | STEP | INSTRUCTIONS
| ASCOPE WORKSHEET TURN IN |  | 2011-02-05 14:30 | 1:00 | 1 |  | 1 | XO CALCULATES TIME AVAILABLE FOR BDE MDMP | 1/3 OF (MISSION EXECUTION-MDMP START TIME)
| MA 1 BRIEF REHEARSAL PREP |  | 2011-02-05 15:30 | 1:00 | 1 |  | 2 | XO COMPLETES CELL C1, D3 AND BLUE SHADED CELLS
| MA 1 BRIEF REHEARSAL & ADJUSTMENTS |  | 2011-02-05 16:30 | 2:00 | 2 |  | 3 | XO ADJUSTS FOR SLEEP TIME, CLASSES, ETC
| MA 1 BRIEF |  | 2011-02-05 18:30 | 1:00 | 1
| REVERSE WFF WORKSHEET TURN IN |  | 2011-02-05 19:30 | 2:00 | 2
| SLEEP TIME |  | 2011-02-05 21:30 | 5:00 | 5 |  |  | In this example the BDE had 300 hours from receipt of mission until execution. The Brigade took 1/3 or 100 hours for MDMP, that left 200 hours for the Battalions, who took 1/3 or 66 hours for MDMP. That left 134 hours left for the Companies who took 1/3 or 44 hours.
| MA WORKSHEET TURN IN |  | 2011-02-06 02:30 | 1:00 | 1
| MA BRIEF 2 REHEARSAL PREP |  | 2011-02-06 03:30 | 2:00 | 2
| MA BRIEF 2 REHEARSAL & ADJUSTMENTS |  | 2011-02-06 05:30 | 1:00 | 1
| MISSION ANALYSIS 2 BRIEFING |  | 2011-02-06 06:30 | 2:00 | 2
| COMMANDER'S TIME |  | 2011-02-06 08:30 | 0:33 | 0.55
| COMMANDER'S GUIDANCE |  | 2011-02-06 09:03 | 0:15 | 0.25
COA DEV 20% | COA DEVELOPMENT |  | 2011-02-06 09:18 | 8:12 | 8.2 | 13.2
| COA BRIEF REHEARSAL & ADJUSTMENTS |  | 2011-02-06 17:30 | 3:00 | 3
| COA BRIEF |  | 2011-02-06 20:30 | 2:00 | 2
WAR-GAMING 30% | SLEEP TIME |  | 2011-02-06 22:30 | 7:00 | 7 | 19.8
| PREP FOR WARGAME |  | 2011-02-07 05:30 | 2:00 | 2
| WARGAME |  | 2011-02-07 07:30 | 7:00 | 7
| COA COMPARISON/DECISION |  | 2011-02-07 14:30 | 3:48 | 3.8
OPORD DEV 20% | OPORD/ANNEXES DEVELOPMENT |  | 2011-02-07 18:18 | 6:00 | 6 | 13.2
| XO REVIEW/RECONCILIATION |  | 2011-02-08 00:18 | 2:00 | 2
| OPORD BRIEFING REHEARSAL & ADJUSTMENTS |  | 2011-02-08 02:18 | 2:00 | 2
| OPORD BRIEFING |  | 2011-02-08 04:18 | 2:00 | 2
| Sub. CDR Confirmation Briefs |  | 2011-02-08 06:18 | 2:00 | 2
| Sub. CDR Backbriefs |  | 2011-02-08 08:18 | 1:00 | 1
| COMPANY TROOP LEADING STEPS AVAILABLE HRS |  | 44
COMPANY/TROOP/BATTERY ACTIVITY
Make Tentative Plan
Initiate Movement
Conduct Recon
Complete Plan
Issue OPORD
Briefbacks
Inspections
Rehearsals
Mission Execution
Formulas:
TIME ACTIVITY STARTS = [TIME ACTIVITY STARTS, row above]+[DURATION UNTIL NEXT EVENT, row above]